## AMERS Backlog
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Checklist Items | Labels | Description
QLgcTO7TbkCIrJ_68jXKSskAIjHK | SPRINT 1 — Dataset & Pipeline Setup | IN PROGRESS | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 12/07/2025 | 12/26/2025 | false | true |  | Select DEAP dataset;Select IEMOCAP dataset;Document channels and annotations;Verify academic license;Define unified emotion labels | Sprint 1;User Story 1 | User Story 1 — Dataset Selection, Documentation & Label Alignment User Story As a researcher, I want to select and document reliable EEG and speech datasets so that the experimental foundation of the system is valid and reproducible. Description This user story covers dataset selection, documentation, and unified emotion label alignment for EEG and speech modalities. Outcome Datasets are selected, documented, and aligned under a common emotion label space. Acceptance Criteria EEG dataset is selected and documented Speech dataset is selected and documented Unified emotion labels are defined Labels are consistently mapped across datasets Documentation is reproducible
oxyj9x-Zd068u-utm2Cs18kAPlyT | SPRINT 1 — Dataset & Pipeline Setup | IN PROGRESS | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 12/17/2025 | 12/26/2025 | false | true |  | Apply LOSO protocol;Define unified emotion labels;Fix random seeds;Run pilot preprocessing;Verify output shapes | Sprint 1;User Story 2 | User Story 2 — Leakage-Free Data Splitting & Pipeline Validation User Story As a researcher, I want to create leakage-free data splits and validate the pipeline so that evaluation results remain unbiased and reliable. Description This user story ensures subject-independent dataset splits and validates the preprocessing pipeline through pilot runs. Outcome Leakage-free dataset splits and a verified preprocessing pipeline. Acceptance Criteria LOSO protocol is implemented No subject or speaker overlap exists Pipeline runs without runtime errors Output data shapes are correct
of1VQ25zLkKCxHjaIiNsJMkAHq1B | SPRINT 2 — EEG Feature Engineering & Baseline Modeling | UP NEXT | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 12/27/2025 | 01/08/2026 | false | true |  | Segment EEG into epochs;Apply band-pass filtering;Perform artifact suppression;Extract EEG features | Sprint 2;User Story 3 | User Story 3 — EEG Preprocessing & Feature Extraction User Story As a system, I want to preprocess EEG signals and extract meaningful features so that emotional patterns can be effectively learned by machine learning models. Description This user story covers EEG signal preprocessing, noise removal, epoching, and feature extraction required for emotion classification. Outcome Clean EEG data and structured feature vectors ready for model training. Acceptance Criteria EEG signals are filtered and cleaned Artifacts are reduced or removed EEG signals are segmented into epochs Feature vectors are generated consistently
E7Y5dKCweUKdCG2uT-RR8ckANzf6 | SPRINT 2 — EEG Feature Engineering & Baseline Modeling | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 01/09/2026 | 01/21/2026 | false | true |  | Implement classifier model;Train model without errors;Compute baseline accuracy and F1-score;Log and save results | Sprint 2;User Story 4 | User Story 4 — Baseline EEG Emotion Classification User Story As a classifier, I want to learn from real EEG feature data so that baseline emotion recognition performance can be established. Description This user story implements and evaluates a baseline EEG emotion classification model without any data augmentation. Outcome Baseline performance metrics for EEG-based emotion recognition. Acceptance Criteria Classifier model is implemented Model trains without errors Baseline accuracy and F1-score are computed Results are logged and saved
hFjxcB-jdE-KH9Nb7LiIGMkAE3MH | SPRINT 3 — GAN-Based EEG Data Augmentation | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 01/22/2026 | 02/01/2026 | false | true |  | Design conditional WGAN-GP architecture;Implement class-conditioned generator and discriminator;Train GAN on EEG feature vectors;Monitor training stability and mode collapse | Sprint 3;User Story 5 | User Story 5 — GAN Architecture Design & Training User Story As a system, I want to generate synthetic EEG features using a GAN model so that data scarcity and class imbalance are reduced. Description This user story designs and trains a conditional Wasserstein GAN with gradient penalty (WGAN-GP) to generate class-conditioned synthetic EEG feature vectors for data augmentation. Outcome A trained GAN capable of producing realistic synthetic EEG features. Acceptance Criteria GAN architecture is implemented Training process is stable Synthetic features match real feature dimensions No severe mode collapse observed
WRodLAcQFkKJDCRk3xn29ckAFpjb | SPRINT 3 — GAN-Based EEG Data Augmentation | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 02/02/2026 | 02/09/2026 | false | true |  | Validate synthetic feature distributions;Apply static GAN augmentation to training set;Train classifier with augmented data;Record and compare performance metrics | Sprint 3;User Story 6 | User Story 6 — Synthetic Data Validation & Static Augmentation User Story As a researcher, I want to validate synthetic EEG features and apply static augmentation so that the effectiveness of GAN-generated data can be evaluated. Description This user story validates GAN-generated features statistically and evaluates classifier performance when trained with synthetically augmented data. Outcome Validated synthetic EEG features and static GAN augmentation results. Acceptance Criteria Synthetic samples are validated statistically Static augmentation is applied correctly Model performance with GAN data is recorded Results are reproducible
kR7nXp3QvUa8bWcLmD4f5skAMn2Y | SPRINT 4 — Contrastive EEG Pretraining | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 02/06/2026 | 02/14/2026 | false | true |  | Implement NT-Xent contrastive loss function;Design EEG augmentation pipeline (noise, scaling, channel dropout);Build projection head for contrastive learning;Train SimCLR on unlabeled EEG data | Sprint 4;User Story 7 | User Story 7 — SimCLR Contrastive Loss & EEG Augmentations User Story As an EEG encoder, I want to learn robust representations through self-supervised contrastive learning so that downstream emotion classification benefits from better feature representations. Description This user story implements the NT-Xent contrastive loss and designs an EEG-specific augmentation pipeline. Two augmented views of the same EEG sample are pulled together while different samples are pushed apart in embedding space. Outcome A contrastive learning framework with EEG-specific augmentations ready for pretraining. Acceptance Criteria NT-Xent contrastive loss is implemented correctly EEG augmentation pipeline includes noise injection, temporal scaling, and channel dropout Projection head maps encoder outputs to contrastive space Loss converges during pretraining
pL9mYr6TwXc2eZfNqG8h1skAJk5W | SPRINT 4 — Contrastive EEG Pretraining | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 02/15/2026 | 02/22/2026 | false | true |  | Run full contrastive pretraining on DEAP;Evaluate encoder quality via linear probe;Compare pretrained vs random initialization;Save pretrained encoder checkpoints | Sprint 4;User Story 8 | User Story 8 — Contrastive Pretraining Execution & Validation User Story As a researcher, I want to validate that contrastive pretraining produces better EEG representations so that downstream tasks benefit from learned features. Description This user story executes SimCLR pretraining on the full DEAP dataset and validates the resulting encoder by measuring downstream emotion classification improvement compared to random initialization. Outcome Pretrained EEG encoder checkpoints with validated representation quality. Acceptance Criteria Contrastive pretraining runs to completion Linear probe accuracy exceeds random initialization baseline Pretrained encoder checkpoint is saved Representation quality is documented
vN2kBs8UyRd5gXhOtJ3i7skAFn9Q | SPRINT 5 — Domain Adversarial Adaptation | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 02/19/2026 | 02/27/2026 | false | true |  | Implement gradient reversal layer;Design domain classifier head;Define emotion classification head;Implement lambda scheduling for domain loss | Sprint 5;User Story 9 | User Story 9 — DANN Architecture & Gradient Reversal Design User Story As a multimodal system, I want a gradient reversal mechanism for domain-adversarial training so that EEG and speech encoders produce domain-invariant representations. Description This user story designs the Domain-Adversarial Neural Network (DANN) components including the gradient reversal layer, domain classifier, emotion head, and lambda scheduling for balancing domain and task losses. Outcome DANN architecture components ready for cross-domain alignment training. Acceptance Criteria Gradient reversal layer is implemented correctly Domain classifier head distinguishes EEG vs speech domains Emotion classification head predicts emotion labels Lambda scheduling balances domain and emotion losses
wQ4lCs9VzSe6hYiPuK5j8skAHp1R | SPRINT 5 — Domain Adversarial Adaptation | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 02/28/2026 | 03/05/2026 | false | false |  | Train DANN on EEG (DEAP) and speech (IEMOCAP);Validate domain-invariant embeddings;Measure domain classification confusion;Save domain-adapted encoder weights | Sprint 5;User Story 10 | User Story 10 — DANN Cross-Domain Alignment Training User Story As a domain adapter, I want to align EEG and speech feature spaces through adversarial training so that downstream fusion can leverage domain-invariant representations. Description This user story trains the DANN model on both EEG (DEAP) and speech (IEMOCAP) data, using adversarial training to make the encoder produce embeddings that are indistinguishable by domain while retaining emotion-discriminative information. Outcome Domain-aligned encoder that produces compatible EEG and speech embeddings. Acceptance Criteria DANN training runs on both modalities Domain classifier confusion increases (alignment improves) Emotion accuracy is maintained or improved Adapted encoder weights are saved
xS6nDt1WARf7iZjQuL7k9skABr3S | SPRINT 6 — Speech Emotion Processing | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 03/02/2026 | 03/09/2026 | false | false |  | Extract MFCC features from IEMOCAP;Implement speech preprocessing pipeline;Design CNN-LSTM speech encoder;Train speech emotion model on IEMOCAP | Sprint 6;User Story 11 | User Story 11 — Speech Feature Extraction & Encoder Training User Story As a speech encoder, I want to process IEMOCAP audio and learn emotion-discriminative features so that speech-based emotion cues complement EEG-based predictions. Description This user story extracts MFCC features from IEMOCAP recordings, designs a CNN-LSTM speech encoder, and trains a speech-only emotion classification model as the speech branch of the multimodal system. Outcome A trained speech encoder with extracted IEMOCAP features. Acceptance Criteria MFCC features are extracted from IEMOCAP correctly Speech preprocessing pipeline handles variable-length audio CNN-LSTM speech encoder is implemented Speech emotion model trains and produces predictions
yT8oEu2XBSg8jAkRvM9l0skACt5T | SPRINT 6 — Speech Emotion Processing | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 03/10/2026 | 03/15/2026 | false | false |  | Implement contrastive speech pretraining;Apply label-aligned EEG-speech pairing;Validate cross-modal pairing quality;Compute speech-only baseline metrics | Sprint 6;User Story 12 | User Story 12 — Speech Pretraining & Cross-Modal Pairing User Story As a multimodal system, I want speech representations pretrained and label-aligned EEG-speech pairs created so that cross-modal fusion receives semantically consistent inputs. Description This user story implements contrastive pretraining for the speech encoder and establishes label-aligned pairing between EEG (DEAP) and speech (IEMOCAP) samples based on emotion class rather than index, ensuring fusion receives consistent supervision signals. Outcome Pretrained speech encoder and label-aligned cross-modal pairs. Acceptance Criteria Contrastive speech pretraining is implemented EEG-speech pairs are aligned by emotion label (not index) Pairing quality is validated Speech-only baseline accuracy is recorded
EN8NueYXgUC9ebzyIs_WIskALAGR | SPRINT 7 — Cross-Modal Fusion Architecture | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 03/12/2026 | 03/19/2026 | false | false |  | Design cross-modal multi-head attention module;Implement gated fusion mechanism;Define focal loss with class weighting;Integrate attention module with pretrained encoders | Sprint 7;User Story 13 | User Story 13 — CMMA Cross-Modal Multi-Head Attention Design User Story As a multimodal classifier, I want to jointly attend to EEG and speech features via cross-modal attention so that inter-modal emotion correlations are captured for better classification. Description This user story designs and implements the Cross-Modal Multi-Head Attention (CMMA) fusion module. EEG attends to speech and speech attends to EEG through multi-head cross-attention, followed by gated fusion and an emotion classification head. Focal loss with class weighting addresses DEAP's 37x class imbalance. Outcome A cross-modal attention fusion architecture integrated with pretrained encoders. Acceptance Criteria Cross-modal multi-head attention architecture is designed Gated fusion mechanism combines attended features Focal loss with sqrt class weighting handles imbalance Module integrates with pretrained EEG and speech encoders
FYN2et-LYkC04FMtb2Sj2ckAGSvh | SPRINT 7 — Cross-Modal Fusion Architecture | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 03/20/2026 | 03/26/2026 | false | false |  | Implement transformer fusion baseline;Compare CMMA vs concatenation vs transformer fusion;Benchmark fusion strategies on validation set;Select best fusion architecture | Sprint 7;User Story 14 | User Story 14 — Fusion Strategy Comparison & Selection User Story As a researcher, I want to compare multiple fusion strategies so that the best-performing architecture is selected for the final pipeline. Description This user story implements and benchmarks multiple fusion approaches: simple concatenation (v1), transformer attention (v3), and CMMA cross-attention (v5). Performance is compared on the validation set to select the final architecture. Outcome Empirical comparison of fusion strategies with CMMA selected as best. Acceptance Criteria Concatenation, transformer, and CMMA fusion are all implemented Each fusion strategy is evaluated on the same validation set Performance comparison is documented Best fusion architecture is selected
aU0pFv3YCSh9kBlSwN1m2skADv7U | SPRINT 8 — End-to-End Pipeline Training & Optimization | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 03/23/2026 | 03/30/2026 | false | false |  | Train end-to-end CMMA pipeline (encoders + fusion + classifier);Implement learning rate scheduling and early stopping;Run iterative architecture versions (v1 through v5);Log performance metrics across all versions | Sprint 8;User Story 15 | User Story 15 — End-to-End CMMA Training & Version Iteration User Story As a system, I want to train the complete CMMA pipeline end-to-end with iterative optimization so that multimodal emotion recognition accuracy is maximized. Description This user story trains the full pipeline (pretrained EEG encoder + pretrained speech encoder + CMMA fusion + classifier) end-to-end. Multiple architecture versions (v1 through v5.3) are trained iteratively, with each version addressing limitations discovered in the previous one. Outcome An optimized multimodal emotion recognition system with documented version progression. Acceptance Criteria End-to-end CMMA pipeline trains without errors Learning rate scheduling and early stopping are applied Multiple versions (v1-v5.3) are trained and compared Best model achieves target accuracy and F1-score
bV1qGw4ZDTi0lCmTxO3n3skAEw8V | SPRINT 8 — End-to-End Pipeline Training & Optimization | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 03/31/2026 | 04/05/2026 | false | false |  | Perform hyperparameter search (learning rate, dropout, attention heads);Tune focal loss gamma and class weight strategy;Optimize batch size and pairing strategy;Record best hyperparameter configuration | Sprint 8;User Story 16 | User Story 16 — Hyperparameter Tuning & Configuration Optimization User Story As a researcher, I want to systematically tune hyperparameters so that the model achieves peak performance under the best configuration. Description This user story performs systematic hyperparameter tuning for the CMMA pipeline including learning rate, dropout rate, number of attention heads, focal loss gamma, class weight strategy (sqrt vs inverse), batch size, and EEG-speech pairing count. Outcome Optimal hyperparameter configuration for the CMMA pipeline. Acceptance Criteria Hyperparameter search covers learning rate, dropout, and attention heads Focal loss gamma and class weight strategy are tuned Batch size and pairing strategy are optimized Best configuration is documented and reproducible
naN5yJwPv0SxicdesFQFYMkAGkH4 | SPRINT 9 — LOSO Subject-Independent Evaluation | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 04/02/2026 | 04/10/2026 | false | false |  | Implement 32-fold LOSO evaluation framework;Run LOSO v1 baseline with global checkpoints;Implement improved LOSO v2 with cross-subject normalization;Compare LOSO v1 and v2 results | Sprint 9;User Story 17 | User Story 17 — LOSO v1 & v2 Implementation User Story As a researcher, I want to evaluate the system using Leave-One-Subject-Out cross-validation so that reported performance reflects true generalization to unseen subjects. Description This user story implements 32-fold LOSO evaluation where each DEAP subject is held out as the test set. LOSO v1 establishes a baseline, while LOSO v2 adds cross-subject normalization, improved class weighting, multi-pairing ensemble, and optimized training for improved subject-independent accuracy. Outcome Subject-independent accuracy with confidence intervals across 32 folds. Acceptance Criteria 32-fold LOSO framework is implemented LOSO v1 baseline results are recorded LOSO v2 with improvements is implemented Per-fold results include mean, std, and per-class metrics
cW2rHx5AETj1mDnUyP5o4skAFx9W | SPRINT 9 — LOSO Subject-Independent Evaluation | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 04/11/2026 | 04/17/2026 | false | false |  | Identify encoder pretraining data leak in LOSO v2;Implement per-fold contrastive pretraining (train subjects only);Implement per-fold DANN training (no global checkpoint);Run strict 32-fold LOSO and compare with leaked results | Sprint 9;User Story 18 | User Story 18 — Strict Leak-Free LOSO Evaluation User Story As a researcher, I want a fully leak-free subject-independent evaluation so that reported accuracy reflects true generalization without any data contamination. Description This user story identifies the encoder pretraining data leak (contrastive + DANN used all 32 subjects) and implements Strict LOSO v2 where ALL pretraining is moved inside the fold loop, ensuring the held-out test subject's data never influences encoder weights. Outcome Unbiased subject-independent accuracy with zero data leakage. Acceptance Criteria Encoder pretraining leak is identified and documented Per-fold contrastive pretraining uses only 30 train subjects Per-fold DANN training uses only train subjects Leak impact is quantified by comparing strict vs standard LOSO
Xs0d0YMKOEaa1YGINc1wxMkAIp56 | SPRINT 10 — Final Evaluation, Ablation & Reporting | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 04/14/2026 | 04/21/2026 | false | false |  | Perform ablation experiments (remove contrastive, DANN, CMMA individually);Compute accuracy, F1-score, UAR, and Cohen's kappa;Generate confusion matrices and per-class metrics;Create result comparison tables across all versions | Sprint 10;User Story 19 | User Story 19 — Ablation Studies & Comprehensive Metrics User Story As a researcher, I want to perform ablation experiments and compute comprehensive metrics so that the contribution of each component is quantified. Description This user story systematically removes individual components (contrastive pretraining, DANN, CMMA, focal loss) and measures the impact on performance. Full metrics including accuracy, macro F1, UAR, and Cohen's kappa are computed for all model versions. Outcome Ablation results quantifying each component's contribution. Acceptance Criteria Ablation removes each component individually All metrics are computed for each ablation variant Results are compared in structured tables Component contributions are clearly quantified
dX3sIy6BFUk2nEoVzQ7p5skAGy0X | SPRINT 10 — Final Evaluation, Ablation & Reporting | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 04/22/2026 | 04/28/2026 | false | false |  | Write LaTeX paper with all results;Generate publication-quality plots and figures;Finalize VERSION_HISTORY documentation;Prepare reproducibility package | Sprint 10;User Story 20 | User Story 20 — Documentation, Paper Writing & Reproducibility User Story As a researcher, I want to document all results and prepare a publication-ready paper so that findings are reproducible and suitable for academic submission. Description This user story finalizes all documentation including the LaTeX research paper, result visualizations, version history, and a reproducibility package that allows others to replicate the experiments. Outcome Complete documentation and publication-ready paper. Acceptance Criteria LaTeX paper includes abstract, methodology, results, and discussion Plots and figures are publication-quality VERSION_HISTORY documents the full v1 to v5.3 progression Experimental setup is fully reproducible