## AMERS Backlog
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Checklist Items | Labels | Description
QLgcTO7TbkCIrJ_68jXKSskAIjHK | SPRINT 1 — Dataset & Pipeline Setup | IN PROGRESS | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 12/07/2025 | 12/26/2025 | false | true |  | Select DEAP dataset;Select IEMOCAP dataset;Document channels and annotations;Verify academic license;Define unified emotion labels | Sprint 1;User Story 1 | User Story 1 — Dataset Selection, Documentation & Label Alignment User Story As a researcher, I want to select and document reliable EEG and speech datasets so that the experimental foundation of the system is valid and reproducible. Description This user story covers dataset selection, documentation, and unified emotion label alignment for EEG and speech modalities. Outcome Datasets are selected, documented, and aligned under a common emotion label space. Acceptance Criteria EEG dataset is selected and documented Speech dataset is selected and documented Unified emotion labels are defined Labels are consistently mapped across datasets Documentation is reproducible
oxyj9x-Zd068u-utm2Cs18kAPlyT | SPRINT 1 — Dataset & Pipeline Setup | IN PROGRESS | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 12/17/2025 | 12/26/2025 | false | true |  | Apply LOSO protocol;Define unified emotion labels;Fix random seeds;Run pilot preprocessing;Verify output shapes | Sprint 1;User Story 2 | User Story 2 — Leakage-Free Data Splitting & Pipeline Validation User Story As a researcher, I want to create leakage-free data splits and validate the pipeline so that evaluation results remain unbiased and reliable. Description This user story ensures subject-independent dataset splits and validates the preprocessing pipeline through pilot runs. Outcome Leakage-free dataset splits and a verified preprocessing pipeline. Acceptance Criteria LOSO protocol is implemented No subject or speaker overlap exists Pipeline runs without runtime errors Output data shapes are correct
of1VQ25zLkKCxHjaIiNsJMkAHq1B | SPRINT 2 — EEG Feature Engineering & Baseline Modeling | UP NEXT | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 12/27/2025 | 01/08/2026 | false | true |  | Segment EEG into epochs;Apply band-pass filtering;Perform artifact suppression;Extract EEG features | Sprint 2;User Story 3 | User Story 3 — EEG Preprocessing & Feature Extraction User Story As a system, I want to preprocess EEG signals and extract meaningful features so that emotional patterns can be effectively learned by machine learning models. Description This user story covers EEG signal preprocessing, noise removal, epoching, and feature extraction required for emotion classification. Outcome Clean EEG data and structured feature vectors ready for model training. Acceptance Criteria EEG signals are filtered and cleaned Artifacts are reduced or removed EEG signals are segmented into epochs Feature vectors are generated consistently
E7Y5dKCweUKdCG2uT-RR8ckANzf6 | SPRINT 2 — EEG Feature Engineering & Baseline Modeling | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 01/09/2026 | 01/21/2026 | false | true |  | Implement classifier model;Train model without errors;Compute baseline accuracy and F1-score;Log and save results | Sprint 2;User Story 4 | User Story 4 — Baseline EEG Emotion Classification User Story As a classifier, I want to learn from real EEG feature data so that baseline emotion recognition performance can be established. Description This user story implements and evaluates a baseline EEG emotion classification model without any data augmentation. Outcome Baseline performance metrics for EEG-based emotion recognition. Acceptance Criteria Classifier model is implemented Model trains without errors Baseline accuracy and F1-score are computed Results are logged and saved
hFjxcB-jdE-KH9Nb7LiIGMkAE3MH | SPRINT 3 — Self-Supervised Pretraining & Domain Adaptation | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 01/21/2026 | 02/02/2026 | false | true |  | Implement NT-Xent contrastive loss;Design EEG augmentation pipeline;Train SimCLR on EEG data;Validate encoder representations | Sprint 3;User Story 5 | User Story 5 — Contrastive EEG Pretraining (SimCLR) User Story As an EEG encoder, I want to learn robust representations through self-supervised contrastive learning so that downstream emotion classification benefits from better feature representations. Description This user story implements SimCLR-style contrastive pretraining for the EEG encoder. Two augmented views of the same EEG sample are pulled together while different samples are pushed apart, learning frequency-band and spatial patterns without labels. Outcome A pretrained EEG encoder with robust representations that transfer to emotion classification. Acceptance Criteria NT-Xent contrastive loss is implemented EEG augmentation pipeline is designed SimCLR pretraining runs successfully Pretrained encoder improves downstream accuracy
WRodLAcQFkKJDCRk3xn29ckAFpjb | SPRINT 3 — Self-Supervised Pretraining & Domain Adaptation | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 02/03/2026 | 02/15/2026 | false | true |  | Implement gradient reversal layer;Design domain classifier head;Train DANN on EEG and speech alignment;Validate domain-invariant embeddings | Sprint 3;User Story 6 | User Story 6 — Domain Adversarial Neural Network (DANN) Training User Story As a multimodal system, I want EEG and speech embeddings aligned in a shared feature space so that cross-modal fusion can leverage domain-invariant representations. Description Domain-Adversarial Neural Network (DANN) uses a gradient reversal layer to train an encoder that fools a domain discriminator, producing embeddings where EEG and speech samples are indistinguishable by domain while retaining emotion-discriminative information. Outcome Domain-aligned EEG encoder that produces embeddings compatible with speech features. Acceptance Criteria Gradient reversal layer is implemented Domain classifier distinguishes EEG vs speech DANN alignment reduces domain gap Downstream emotion accuracy improves with aligned embeddings
EN8NueYXgUC9ebzyIs_WIskALAGR | SPRINT 4 — Cross-Modal Fusion Architecture | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 02/16/2026 | 02/24/2026 | false | true |  | Design cross-modal multi-head attention;Implement gated fusion mechanism;Define focal loss with class weighting;Integrate with pretrained encoders | Sprint 4;User Story 7 | User Story 7 — CMMA Cross-Modal Multi-Head Attention Design User Story As a multimodal classifier, I want to jointly attend to EEG and speech features via cross-modal attention so that inter-modal emotion correlations are captured for better classification. Description This user story designs and implements the Cross-Modal Multi-Head Attention (CMMA) fusion module. EEG attends to speech and speech attends to EEG through multi-head cross-attention, followed by gated fusion and emotion classification. Outcome A cross-modal attention fusion architecture ready for end-to-end training. Acceptance Criteria Cross-modal attention architecture is designed Gated fusion mechanism is implemented Focal loss with class weighting handles imbalance Module integrates with pretrained EEG and speech encoders
FYN2et-LYkC04FMtb2Sj2ckAGSvh | SPRINT 4 — Cross-Modal Fusion Architecture | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 02/25/2026 | 03/03/2026 | false | false |  | Train end-to-end CMMA pipeline;Perform hyperparameter tuning;Run iterative architecture versions;Log performance across versions | Sprint 4;User Story 8 | User Story 8 — End-to-End CMMA Training & Optimization User Story As a system, I want to train the complete CMMA pipeline end-to-end with iterative optimization so that multimodal emotion recognition accuracy is maximized. Description This user story trains the full pipeline (pretrained encoders + CMMA fusion + classifier) end-to-end with label-aligned EEG-speech pairing, focal loss, and learning rate scheduling. Multiple architecture versions (v1 through v5.3) are evaluated iteratively. Outcome An optimized multimodal emotion recognition system achieving target accuracy. Acceptance Criteria End-to-end CMMA pipeline trains without errors Hyperparameter tuning is performed systematically Multiple versions are evaluated and compared Best model achieves target accuracy and F1-score
naN5yJwPv0SxicdesFQFYMkAGkH4 | SPRINT 5 — Evaluation, LOSO & Reporting | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 03/06/2026 | 03/13/2026 | false | false |  | Implement 32-fold LOSO evaluation;Build strict leak-free LOSO pipeline;Run subject-independent cross-validation;Compare LOSO variants and quantify leak impact | Sprint 5;User Story 9 | User Story 9 — Subject-Independent LOSO Evaluation User Story As a researcher, I want to evaluate the system using Leave-One-Subject-Out cross-validation so that reported performance reflects true generalization to unseen subjects. Description This user story implements 32-fold LOSO evaluation where each DEAP subject is held out as the test set. It includes both standard LOSO and a strict leak-free variant that moves all pretraining inside the fold loop to ensure zero data contamination. Outcome Subject-independent accuracy with confidence intervals and leak-free validation. Acceptance Criteria 32-fold LOSO evaluation is implemented Strict leak-free LOSO variant is implemented Per-fold results are logged with confidence intervals Leak impact is quantified by comparing LOSO variants
Xs0d0YMKOEaa1YGINc1wxMkAIp56 | SPRINT 5 — Evaluation, LOSO & Reporting | BACKLOG | Not started | Medium | RAVINDRA JONNAGADLA (RA2211028010187);NIKETH VATTUMILLI (RA2211028010144) | RAVINDRA JONNAGADLA (RA2211028010187) | 01/05/2026 | 03/14/2026 | 03/20/2026 | false | false |  | Perform ablation experiments;Compute accuracy, F1-score, UAR, and Cohen's kappa;Generate result tables and plots;Finalize documentation and paper | Sprint 5;User Story 10 | User Story 10 — Final Evaluation, Ablation & Documentation User Story As a researcher, I want to evaluate the complete system and document results so that findings are reproducible and suitable for academic submission. Description This user story performs final evaluation, ablation studies, and prepares structured documentation of results. Outcome Final results, analysis, and documentation ready for review or publication. Acceptance Criteria Evaluation metrics are computed correctly Ablation studies are completed Results are clearly documented Experimental setup is reproducible